## Activity.WorkBreakdownStructure
WBS ID | Level | Task/Work Package Name | Duration | Dependencies (WBS ID & Name) | DAVID DOMINGUEZ
1 |  | Project Planning (Deliverable) |  |  | CIS 4860
1.1 | Work Package | Project Plan Development | 2 days total
1.1.1 | Task | Gather requirements | 2 days
1.1.2 | Task | Identify stakeholders | 1 day
1.1.3 | Task | Risk assesment | 1 day
1.1.4 | Task | Define scope | 1 day
1.1.5 | Task | Set milestones | 1 day
1.1.6 | Task | Develop Budget | 1 day
1.1.7 | Task | Approval of plan | 1 day
1.2 | Work Package | Define project objectives | 1 day total
1.2.1 | Task | Align objectives with stakeholders | 1 day
1.2.2 | Task | Document objectives | 1 day
1.3 | Work Package | Create project timeline | 1 day total
1.3.1 | Task | Schedule meetings | 1 day
1.3.2 | Task | Finalize timeline | 1 day
1.4 | Work Package | Allocate resources | 1 day total
1.4.1 | Task | Assign team roles | 1 day
1.4.2 | Task | Resource procurement | 1 day
1.4.3 | Task | Confirm resource availability | 1 day
2 |  | Website Design Mockup (Deliverable)
2.1 | Work Package | Design creation | 5 days total
2.1.1 | Task | Develop homepage mockup | 5 days
2.1.1.1 | Task | Sketch initial design | 2 days | 2.1.1.1 ¦¦ 2.1.1.2
2.1.1.2 | Task | Create wireframe | 2 days
2.1.1.3 | Task | Design visual elements | 1 day
2.1.2 | Task | Design additional pages | 5 days | dependent on 2.1.1 Develop homepage mockup
2.1.2.1 | Task | Layout design | 2 days
2.1.2.2 | Task | Color scheme selection | 1 day
2.1.2.3 | Task | Typography selection | 1 day
2.1.2.4 | Task | Image selection | 1 day
2.1.3 | Task | Review and incorporate feedback | 3 days | dependent on 2.1.2 Design additional pages
2.1.3.1 | Task | Conduct design review | 1 day
2.1.3.2 | Task | Gather feedback | 1 day
2.1.3.3 | Task | Implement changes | 1 day
3 |  | Content Development (Deliverable)
3.1 | Work Package | Content Writing | 5 days total
3.1.1 | Task | Write homepage content | 5 days
3.1.1.1 | Task | Draft initial content | 2 days
3.1.1.2 | Task | Edit and revise | 2days
3.1.1.3 | Task | Finalize content | 1 day
3.1.2 | Task | Write about page content | 5 days | dependent on 3.1.2
3.1.3.1 | Task | Identify services | 2 days
3.1.3.2 | Task | Draft content | 2 days
3.1.3.3 | Task | Edit and revise | 1 day
3.1.4 | Task | Write contact page content | 5 days | dependent on 3.1.3
3.1.4.1 | Task | Draft contact information | 2 days
3.1.4.2 | Task | Edit and revise | 2 days
3.1.4.3 | Task | Finalize content | 1 day
4 |  | Website Development (Deliverable)
4.1 | Work Package | Technical Development | 5 days total
4.1.1 | Task | Code homepage | 5 days
4.1.1.1 | Task | Setup development environment | 2 days | 4.1.1.1 ¦¦ 4.1.1.2
4.1.1.2 | Task | Implement HTML structure | 2 days
4.1.1.3 | Task | Style with CSS | 1 day
4.1.2 | Task | Code additional pages | 5 days | 4.1.2 dependent on 4.1.1 Code homepage
4.1.2.1 | Task | Implement HTML structure | 2 days
4.1.2.2 | Task | Style with CSS | 2 days
4.1.2.3 | Task | Add Javascript functionality | 1 day
4.1.3 |  | Implement responsive design | 5 days | 4.1.3 dependent on 4.1.2 Code additional pages
4.1.3.1 | Task | Media queries setup | 2 days
4.1.3.2 | Task | Test on multiple devices | 2 days
4.1.3.3 | Task | Optimize performance | 1 day
5 |  | Conduct Functionality Review (Deliverable)
5.1 | Work Package | Collect Feedback for Improvements | 1 day total
5.1.1 | Task | Conduct user testing | 1 day
5.1.2 | Task | Gather user feedback | 1 day
5.1.3 | Task | Analyze feedback | 1 day
5.1.4 | Task | Plan Improvements | 1 day